## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 26.04.2021 - 21:00
Group Number
Participant 1 |  | Saifee
Participant 2 |  | Awan
Participant 3 |  | Yang
Participant 4 |  | Coskun
Participant 5 |  | Amir
Mentor |  | Holweg
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
8 | Prototype - Homepage |  |  | 0 | 1
9 | Prototype - Admin Dashboard | 1 | 1 | 0 | 1
10 | Prototype - Admin Sales |  |  | 0 | 1
11 | Prototype - Admin Users | 2.5 | 2 | -0.5 | 1
12 | Prototype - Admin Products | 1 | 1.5 | 0.5 | 1
13 | Prototype - Admin Profile | 1.5 |  | -1.5 | 1
14 | Prototype - Category | 1.5 |  | -1.5 | 1
15 | Prototype - Contact Us | 2.5 | 2 | -0.5 | 1
16 | Prototype - About Us | 1 | 1 | 0 | 1
17 | Prototype - Login & Register | 1 | 1.5 | 0.5 | 1
18 | Wie habt ihr euch im Sprint 3 getan? | 2.5 | 0.5 | -2 | 1
19 | Gabs irgendwelche Probleme bei Sprint 3? | 2.5 | 0.5 | -2 | 1
20 | Sonstige Fragen, Beschwerden, Wünsche? | 1 | 0.25 | -0.75 | 1
21 |  |  |  | 0
22 |  |  |  | 0
23 |  |  |  | 0
24 |  |  |  | 0
17 |  |  |  | -7.75 | 13 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol