## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 11.05.2021, 20:00
Group Number |  | 12
Participant 1 |  | Saifee
Participant 2 |  | Awan
Participant 3 |  | Coskun
Participant 4 |  | Yang
Participant 5 |  | Amir
Mentor |  | Holweg
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
22 | Aufwandsschätzung | 6 | 5 | -1
23 | Top Menu |  |  | 0
24 | Main Menu |  |  | 0
26 | Slider |  |  | 0
27 | Intro Box |  |  | 0
29 | User - Registration |  |  | 0
30 | MyAcc Page |  |  | 0
32 | DB Creation |  |  | 0
33 | DB Connection |  |  | 0
88 | Gantt Diagramm | 2 |  | -2
10 |  |  |  | -3 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol