## Tabelle1
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 24.05.2021, 20:00
Group Number |  | 12
Participant 1 |  | Saifee
Participant 2 |  | Awan
Participant 3 |  | Yang
Participant 4 |  | Amir
Participant 5 |  | Coskun
Mentor |  | Holweg
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
35 | .) Product Storefront | 5 | 3.5 | -1.5 | 1
36 | .) Footer | 1.3 | 2 | 0.7 | 1
39 | .) Cart | 3 | 4 | 1 | 1
40 | .) Shop | 3 | 5 | 2 | 1
41 | .) Product Details | 2 | 2 | 0 | 1
38 | .) Contact Form | 1 | 1 | 0 | 1
43 | .) Create Table | 2.5 | 2.5 | 0 | 1
44 | .) Connect & Manage | 1 | 1 | 0 | 1
45 | .) Create Frontend | 3 | 3 | 0 | 1
70 | .) Admin Panel - Product Category | 3 | 2.5 | -0.5 | 1
71 | .) Admin Panel - Edit Products |  |  | 0 | 1
51 | .) Shop Page | 2 | 2 | 0 | 1
52 | .) Detail Page | 1.5 | 2.5 | 1 | 1
53 | .) Total Item | 1 | 1.5 | 0.5 | 1
54 | .) Price | 1 | 1 | 0 | 1
58 | .) Cart Page | 1 | 2 | 1 | 1
56 | .) Registrierungsformular | 1.5 | 2 | 0.5 | 1
57 | .) Kontaktformular | 1 | 1 | 0 | 1
60 | .) Product Request | 2 | 1.5 | -0.5 | 1
82 | .) Create Panel | 1 | 1.5 | 0.5 | 1
62 | .) Nav Menu | 3 | 2.5 | -0.5 | 1
64 | .) Login/Logout | 7 | 5 | -2 | 1
68 | .) Customers & Orders | 2 | 2.5 | 0.5 | 1
72 | .) Sliders | 6 | 4 | -2 | 1
66 | .) Create Dashboard | 8 | 8 | 0 | 1
67 | .) Dynamical Design | 5.5 | 8 | 2.5 | 1
26 |  |  |  | 3.2 | 26 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol